## North Wales 2017_18
North Wales Intermittent and Capital Maintenance Programme 2017/18
FRMS code (FR/**/S***) | FRMS name | Local Authority | Catchment Flood Management Plan (CFMP) name | Shorline Management Plan (SMP) name | Job name | Description of work | NGR | Primary purpose | Secondary purpose | Asset type | Q1 work planned (%) | Q2 work planned (%) | Q3 work planned (%) | Q4 work planned (%)
FR/18/S087 | Harlech & Maentwrog | Gwynedd CC | North West Wales | West of Wales | Ty Gwyn tidal doors replacement | Refurbishing structure and replacing tidal doors | SH 59963 35468 | Flood risk | H&S/Legal/Statutory | Structure |  | 50% | 50%
FR/18/S092 | Dolgellau & Fairbourne | Gwynedd CC | North West Wales | West of Wales | Fairbourne sea defence protection | Beach recharge from North to South to protect the sea wall. | SH 61098 12026 | Flood risk | H&S/Legal/Statutory | Raised defence |  |  | 100%
FR/18/S087 | Harlech & Maentwrog | Gwynedd CC | North West Wales | West of Wales | Harlech weedscreen | New weedscreen on Ffos Ddwr | SH 58009 31374 | Flood risk | H&S/Legal/Statutory | Structure | 100%
FR/18/S087 | Harlech & Maentwrog | Gwynedd CC | North West Wales | West of Wales | Draenogan tidal outfall | Outfall and culvert replacement | SH 60314 35511 | Flood risk | H&S/Legal/Statutory | Structure |  | 100%
FR/18/S084 | Rhyd Hir and Erch | Gwynedd CC | North West Wales | West of Wales | Abererch embankment repair | Improvements to existing flood bank adjacent to the Builders Yard | SH 39757 36744 | Flood risk | Erosion | Raised defence |  | 100%
FR/18/S084 | Rhyd Hir and Erch | Gwynedd CC | North West Wales | West of Wales | Abererch Dunes rock armour repair | Realign dsiplaced boulders along a 400 metre section at Aberech Dunes | SH 39485 35847 | Flood risk | Erosion | Raised defence | 100%
FR/18/S081 | Foryd | Gwynedd CC | North West Wales | West of Wales | Dinas Dinlle marker post | Repair storm damage marker post on Dians Dinlle beach groyne | SH 43467 56968 | H&S/Legal/Statutory |  | Structure | 100%
FR/18/S069 | Cefni | Sir Ynys Mon - Isle of Anglesey | North West Wales | West of Wales | Malltraeth stone pitching | Repairs to stone pitching on left hand bank and right hand bank between railway viaduct and Malltraeth High Street. | SH4076368711 | Flood risk | Erosion | Raised defence |  | 50% | 50%
FR/18/S069 | Cefni | Sir Ynys Mon - Isle of Anglesey | North West Wales | West of Wales | Malltraeth structure repair | Repairs to concrete panels in the Telford Tidal Door compound. | SH4076368711 | Flood risk | Erosion | Structure |  | 100%
FR/18/S076 | Lower Conwy | Conwy CBC | Conwy and Clwyd | West of Wales | Whitebarn South embankment | Replacing outfall flap and culvert from field drain through reservoir spillway | SH 78484 63542 | H&S/Legal/Statutory | Flood risk | Raised defence |  | 100%
FR/18/S047 | St Asaph | Denbighshire | Conwy and Clwyd | North Wales | River Elwy erosion, upstream of Pentre Uchaf | Works is to include bank stabiliasation to protect the toe of the Right hand Flood Embankment. Length of repair is approx 10meters in length. | SJ0321375860 | Flood risk | Erosion | Raised defence | 0% | 100% | 0% | 0%
FR/18/S046 | Rhyl | Denbighshire | Conwy and Clwyd | North Wales | Rhyl Cut access improvements | Carry out works to improve access for mechanical means through certain sections of the Rhyl Cut. Start from Junction at Ffordd Las and Cefndy Road ~SJ0114480544, Finish at Grange Road ~SJ0173281346. Existing fencing to moved/replaced, gates incorpated and vegetation/tree work undertaken to allow access. | SJ0114480544 to SJ0173281346 | Flood risk | H&S/Legal/Statutory | Channel | 25% | 25% | 25% | 25%
FR18/S017 | Wepre & Rowleys | Flintshire | Dee | North Wales | Rowleys weedscreen and gantry works | Works will involve the installation of new weed screen and gantry on the inlet to pumping station. The works will also include the minor civil works in the form of access steps and a ramp for future maintenance activities. | SJ 31544 68872 | H&S/Legal/Statutory | Flood risk | Structure |  |  | 40% | 60%
FR18/S015 | Queensferry and Highier ferry | Flintshire | Dee | North Wales | Beeches outfall | AMX Ref - CO1700022 ( Currently P1 ) secondary flap in none working condition any works here in the form of structural reports would also need to incorporate the primary outfall which is also a P2 Defect. | SJ 35319 66698 | Flood risk | H&S/Legal/Statutory | Structure | 25% | 25% | 25% | 25%
FR18/S015 | Queensferry and Highier ferry | Flintshire | Dee | North Wales | Hawarden embankment repairs | AMX Ref - AN1600005 (Currently P2)- Badger eviction and access improvement works next to scarp yard. | SJ 34189 67385 | Flood risk | Erosion | Raised defence |  | 30% | 70%
FR18/S022 | Pontblyddyn | Flintshire | Alyn | North Wales | Pontblyddyn health and safety improvement works | Works will involve the construction of a collection area for wagon and grab, following operatives reporting manual issues | SJ 27601 60425 | H&S/Legal/Statutory | Flood risk | Structure |  |  | 40% | 60%
Note on A1: Kelland, Richard: